## discipline (hidden)
Discipline | Hostname
E&I | https://maximo.biendongpoc.vn
MECH | https://bdpqp-maxapp.biendongpoc.vn
RES
DECK
PROD
*

## PTW
Work Order Scheduler | [6 empty] | Target Date From: |  | 2025-12-01 | Target Date To: | 43921 | 2026-01-01 | Total Plan Hours: |  | 3751.8333
% Complete | Discipline | Work Order | Description | Prepare PTW | Justify note | Work Type | Tag Name | System ID | Scheduled Start | Scheduled Finish | Actual Start | Actual Finish | Status | Priority | Onshore PIC | Assigned PIC | Est. Duration | Justify for duration | Target Start | Target Finish | WOID | Upload? | Change Target?
0% | E&I | P13460410 | Replace bearing for the motor HT-FNM-7161A due to running with high noise |  |  | REC | HT-FNM-7161A | PQP-HVAC |  |  |  |  | APPR | High (3) | CONGNP | HAIDQ | 55 | 0 | 2025-12-01 11:02 | 2025-12-31 11:02 | 503169 | Y | N
0% | E&I | P13463469 | Check and fix HT-FIT-8010 no signal |  | Chưa có vật tư | CM | HT-FIT-8010 | HT-80-FIRE-WATER |  |  |  |  | APPR | Medium (2) |  |  | 7 | 0 | 2025-12-01 13:37 | 2025-12-31 13:37 | 523859 | Y | N
0% | E&I | P13431393 | Need to be replaced new heater with bundle for Heating medium heater |  | Chưa có vật tư | OVERHAUL | HT-HM | HT-42-HEATINGMEDIUM |  |  |  |  | WMATL | Medium (2) | CONGNP |  | 300 | 0 | 2025-12-01 11:19 | 2025-12-31 15:10 | 254285 | Y | N
0% | E&I | P13462716 | Follow Up WO: P13445867 Implement TCR HT-01-TCR-0352 To install the additional Calibration Ring for MT1-PZT-0110F | TuenNH |  | MoD | MT1-PZT-0110F | MT1-01-WHC-SYSTEM |  |  |  |  | WMATL | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-01 06:30 | 2025-12-31 07:40 | 522289 | Y | N
0% | E&I | P13462960 | Order material for replace lighting fixture inside LQ to Duhal LED |  | Chưa có vật tư | General | HT-ES | HT-77-ELECT-SYS |  |  |  |  | WMATL | Medium (2) |  |  | 5 | 0 | 2025-12-01 06:30 | 2025-12-31 06:30 | 522801 | Y | N
0% | E&I | P13462398 | Replace the damaged cooling fan covers on the motors |  | Chưa có vật tư | General | MT1-PM-6760A | MT1-67-SEWAGE-SYSTEM |  |  |  |  | WMATL | Medium (2) |  |  | 10.5 | 0 | 2025-09-01 16:23 | 2025-12-31 16:23 | 520609 | Y | N
0% | E&I | P13460422 | Purchase hot spare for Downhole gauge monitoring system |  | Chưa có vật tư | General | HT-DHG-9810 | HT-98-MISC-SYSTEM |  |  |  |  | WMATL | Medium (2) | SONNM |  | 1 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 503221 | Y | N
0% | E&I | P13461326 | Replace pressure gauge MT1-PG-8031A due to failure |  | Chưa có vật tư | General | MT1-PG-8031A | MT1-80-FIRE-WATER |  |  |  |  | WMATL | Medium (2) |  |  | 2 | 0 | 2025-10-01 10:19 | 2025-12-31 15:35 | 512649 | Y | N
0% | E&I | P13461331 | Replace Temperature gauge MT1-TI-8015A due to failure |  | Chưa có vật tư | General | MT1-TG-8015A | MT1-80-FIRE-WATER |  |  |  |  | WMATL | Medium (2) |  |  | 2 | 0 | 2025-10-01 12:54 | 2025-12-31 15:35 | 512769 | Y | N
0% | E&I | P13465316 | Troubleshoot Switch MT1-RTR-9110 due to not operating | TuenNH |  | CM | MT1 | [5 empty] | WMATL | Medium (2) |  |  | 6 | 6 | 2025-12-01 08:11 | 2025-12-31 08:12 | 527685 | Y | N
0% | E&I | P13463520 | HT-PM-5610B Motor foot was broken need to fabrication new one & replace bearing |  | Chưa có vật tư | CM | HT-PM-5610B | HT-56-OPEN-DRAIN | 2025-08-01 16:17 | 2025-12-31 16:17 |  |  | WMATL | Medium (2) | CONGNP |  | 20 | 0 | 2025-08-01 16:17 | 2025-12-31 16:17 | 523961 | N | N
0% | E&I | P13465665 | Replace Air shutoff solenoid of HT-CR-7321 North Crane |  | Chưa có vật tư | CM | HT-CR-7321 | HT-73-MECHHANDLING | 2025-11-01 06:30 | 2025-12-31 11:00 |  |  | WMATL | Medium (2) |  |  | 12 | 0 | 2025-11-01 06:30 | 2025-12-31 11:00 | 528403 | N | N
0% | E&I | H14176582 | Weekly service routine for MT1 Lifeboat, Fire water pump, EDG, Helicopter Starter Box, MT1-LB-8601 | TuenNH |  | Routine | MT1-LB-8601 | MT1-82-DELUGE-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 50 | 50 | 2025-12-01 | 2025-12-31 | 2237458 | Y | N
0% | E&I | H14176265 | 3M - Function Test all Speakers and Beacons of PAGA Sytstem B on MT1, MT1-PAGB | TuenNH |  | PM | MT1-PAGB | MT1-90-TELECOM-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2236824 | Y | NOT ALLOW
0% | E&I | H14176263 | 3M - Function Test all Speakers and Beacons of PAGA Sytstem A on MT1, MT1-PAGA | TuenNH |  | PM | MT1-PAGA | MT1-90-TELECOM-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2236820 | Y | NOT ALLOW
0% | E&I | H14176255 | 3M - Function Test all Speakers and Beacons of PAGA Sytstem B on PQP and HT1, HT-PAGA-B |  | Radio làm | PM | HT-PAGA-B | HT-90-TELECOM-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 0 | 2025-12-01 | 2025-12-31 | 2236804 | Y | NOT ALLOW
0% | E&I | H14176697 | 12M PM and CFT Fire and Gas devices at Level 1 of LQ, HT-LEVEL1 | HaiDQ |  | PM | HT-LEVEL1 | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 24 | 24 | 2025-12-03 | 2025-12-31 | 2237688 | Y | NOT ALLOW
0% | E&I | H14176253 | 3M - Function Test all Speakers and Beacons of PAGA Sytstem A on PQP and HT1, HT-PAGA-A |  | Radio làm | PM | HT-PAGA-A | HT-90-TELECOM-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 0 | 2025-12-01 | 2025-12-31 | 2236800 | Y | NOT ALLOW
0% | E&I | H14177291 | Weekly service routine for system 86 PQP Lifeboat , EDG, fire pump, helicopter starter box, HT-SE | BanPV |  | PM | HT-SE | HT-82-DELUGE-SYSTEM |  |  |  |  | SCHED | Medium (2) |  |  | 50 | 50 | 2025-12-18 | 2025-12-31 | 2238876 | Y | NOT ALLOW
0% | E&I | H14176825 | 12M PM and CFT Fire and Gas devices at Level 2 of LQ, HT-LEVEL2 | HaiDQ |  | PM | HT-LEVEL2 | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-03 | 2025-12-31 | 2237944 | Y | NOT ALLOW
0% | E&I | H14176990 | 12M PM and CFT Fire & Gas deives at Electrical Building, HT-EB | HaiDQ |  | PM | HT-EB | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-03 | 2025-12-31 | 2238274 | Y | NOT ALLOW
0% | E&I | H14176640 | 12M PM and CFT Fire and Gas devices at CCR and GO, HT-A01 | HAiDQ |  | PM | HT-A01 | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-03 | 2025-12-31 | 2237574 | Y | NOT ALLOW
0% | E&I | H14176378 | 12M PM and CFT Fire and Gas devices at Tel & IER Room, Store & Lab Room, HT-A01 | HaiDQ |  | PM | HT-A01 | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-01 | 2025-12-31 | 2237050 | Y | NOT ALLOW
0% | E&I | H14176900 | 12M PM and CFT Fire and Gas devices at Level 3 of LQ, HT-LEVEL3 | HaiDQ |  | PM | HT-LEVEL3 | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-03 | 2025-12-31 | 2238094 | Y | NOT ALLOW
0% | E&I | H14177065 | 12M PM AFGS controller, HT-FG | MinhNC |  | PM | HT-FG | HT-97-FIRE-GAS-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 18 | 18 | 2025-12-03 | 2025-12-31 | 2238424 | Y | NOT ALLOW
0% | E&I | H14175288 | 06M - PM for system PQP HT-SK-4930, HT-LZT-4930 | NgocNH |  | PM | HT-LZT-4930 | HT-49-CHEM-INJECT |  |  |  |  | SCHED | Medium (2) |  |  | 3 | 3 | 2025-12-01 | 2025-12-31 | 2234870 | Y | NOT ALLOW
0% | E&I | H14177478 | 12M - PM Well head slot 04 MT1, MT1-WH-0104 | TuenNH |  | PM | MT1-WH-0104 | MT1-01-WHC-SYSTEM |  |  |  |  | SCHED | Medium (2) |  |  | 29.5 | 29.5 | 2025-12-27 | 2025-12-31 | 2239290 | Y | NOT ALLOW
0% | E&I | H14176348 | 06M - Maintenance and Critical Function Test SLOT 01, HT1-WH-0101 | MinhND |  | PM | HT1-WH-0101 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2236990 | Y | NOT ALLOW
0% | E&I | H14176172 | 12M - PM for system 49: Electrical devices, HT1-CIS | BanPV |  | PM | HT1-CIS | HT1-49-CHEM-INJECT |  |  |  |  | SCHED | Medium (2) |  |  | 90 | 90 | 2025-12-01 | 2025-12-31 | 2236638 | Y | NOT ALLOW
0% | E&I | H14176604 | 3M - Rotate shaft of spare motor in VTB by hand, |  |  | PM | [6 empty] | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-01 | 2025-12-31 | 2237502 | Y | NOT ALLOW
0% | E&I | H14176600 | Inspection / send to shore for Re-certification E&I portable tools, HT-WE-EI-TOOLS |  |  | PM | HT-WE-EI-TOOLS | HT-72-WORKSHOPEQUIP |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2237494 | Y | NOT ALLOW
0% | E&I | H14176333 | 06M - Maintenance and Critical Function Test SLOT 16, HT1-WH-0116 | MinhND |  | PM | HT1-WH-0116 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2236960 | Y | NOT ALLOW
0% | E&I | H14177618 | 12M - Maintenance and Critical Function Test SLOT 03 HT1, HT1-WH-0103 | NgocNH | New justify | PM | HT1-WH-0103 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 40 | 21 | 2025-12-28 | 2025-12-31 | 2239570 | Y | NOT ALLOW
0% | E&I | H14177370 | 12M - PM Well head slot 02 MT1, MT1-WH-0102 | TuenNH |  | PM | MT1-WH-0102 | MT1-01-WHC-SYSTEM |  |  |  |  | SCHED | Medium (2) |  |  | 33 | 33 | 2025-12-27 | 2025-12-31 | 2239074 | Y | NOT ALLOW
0% | E&I | H14177192 | 3M Backup data package, PQP | TapTV |  | PM | PQP | [5 empty] | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-09 | 2025-12-31 | 2238678 | Y | NOT ALLOW
0% | E&I | H14177774 | 12M - Maintenance and Critical Function Test SLOT 07, HT1-WH-0107 | ThangTD | New justify | PM | HT1-WH-0107 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 40 | 21 | 2025-12-30 | 2025-12-31 | 2239882 | Y | NOT ALLOW
0% | E&I | H14176318 | 06M - Maintenance and Critical Function Test SLOT 07, HT1-WH-0107 | MinhND |  | PM | HT1-WH-0107 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2236930 | Y | NOT ALLOW
0% | E&I | H14176303 | 06M - Maintenance and Critical Function Test SLOT 06, HT1-WH-0106 | MinhND |  | PM | HT1-WH-0106 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 5.5 | 5.5 | 2025-12-01 | 2025-12-31 | 2236900 | Y | NOT ALLOW
0% | E&I | H14177255 | Weekly Service routine for Metering System, HT-SK-2800 | TapTV |  | PM | HT-SK-2800 | HT-26-GAS-EXP-COMPS |  |  |  |  | SCHED | Medium (2) |  |  | 12 | 12 | 2025-12-15 | 2025-12-31 | 2238804 | Y | NOT ALLOW
0% | E&I | H14177915 | 12M - Maintenance and Critical Function Test SLOT 16, HT1-WH-0116 | NgocNH | New justify | PM | HT1-WH-0116 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 40 | 21 | 2025-12-31 | 2025-12-31 | 2240190 | Y | NOT ALLOW
0% | E&I | H14177245 | Monthly Serial check and Diagnostic USM, HT-GM | TapTV |  | PM | HT-GM | HT-28-GAS-METERING |  |  |  |  | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-15 | 2025-12-31 | 2238784 | Y | NOT ALLOW
0% | E&I | H14176464 | 6M - Maintenance and Critical Function Test Open Drain HT1, HT1-HODS | ThangTD |  | PM | HT1-HODS | HT1-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2237222 | Y | NOT ALLOW
0% | E&I | H14176288 | 06M - Maintenance and Critical Function Test SLOT 11, HT1-WH-0111 | MinhND |  | PM | HT1-WH-0111 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2236870 | Y | NOT ALLOW
0% | E&I | H14176363 | 06M - Maintenance and Critical Function Test SLOT 03, HT1-WH-0103 | MinhND |  | PM | HT1-WH-0103 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 5.5 | 5.5 | 2025-12-01 | 2025-12-31 | 2237020 | Y | NOT ALLOW
0% | E&I | H14176267 | 06M - Maintenance and Critical Function Test HT1-WHCP, HT1-WCP | ThangTD |  | PM | HT1-WCP | HT1-01-WHC-SYSTEM |  |  |  |  | SCHED | Medium (2) |  |  | 10.5 | 10.5 | 2025-12-01 | 2025-12-31 | 2236828 | Y | NOT ALLOW
0% | E&I | H14186917 | Monthly monitoring for transformers MT1-TX-7751 750kVA 11/0.433Kv TransFormer, MT1-TX-7751 | TuenNH |  | PM | MT1-TX-7751 | MT1-77-ELECT-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 0.2 | 0.2 | 2025-12-08 | 2025-12-31 | 2258302 | Y | NOT ALLOW
0% | E&I | H14186905 | Monthly monitoring for PQP transformer, HT-ES | TapTV |  | PM | HT-ES | HT-77-ELECT-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 1 | 1 | 2025-12-08 | 2025-12-31 | 2258278 | Y | NOT ALLOW
0% | E&I | H14186835 | Monthly and Weekly routine diagnostic and check ICSS, HT-PCS-9600 |  |  | PM | HT-PCS-9600 | HT-96-PCS-SYSTEM |  |  |  |  | SCHED | Medium (2) |  |  | 30 | 30 | 2025-12-07 | 2025-12-31 | 2258138 | Y | NOT ALLOW
0% | E&I | H14174601 | 12M - Maintenance and Functional Test Electrical devices for MT1 Diesel Storge and Distribution System, MT1-DSAD | TuenNH |  | PM | MT1-DSAD | MT1-63-DIESELSTORAGE |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2233496 | Y | NOT ALLOW
0% | E&I | H14174428 | 6M - Maintenance and Critical Function Test Closed Drain PQP, HT-V-5510 | ThangTD |  | PM | HT-V-5510 | HT-55-CLOSED-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-01 | 2025-12-31 | 2233150 | Y | NOT ALLOW
0% | E&I | H14175274 | 12M - PM for system 98XX - Miscellaneous INSTRUMENTATION, MT1 | TuenNH |  | PM | MT1 | [5 empty] | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2234842 | Y | NOT ALLOW
0% | E&I | H14174251 | 6M - Maintenance and CFT SDS Instrument devices Fuel Gas train A PQP, HT-SK-4000A | ThangTD |  | PM | HT-SK-4000A | HT-40-FUEL-GAS |  |  |  |  | SCHED | Medium (2) |  |  | 16 | 16 | 2025-12-01 | 2025-12-31 | 2232796 | Y | NOT ALLOW
0% | E&I | H14175270 | 12M - PM for system 96XX MT1-LQOWS-01, MT1 | TuenNH |  | PM | MT1 | [5 empty] | SCHED | Medium (2) |  |  | 5 | 5 | 2025-12-01 | 2025-12-31 | 2234834 | Y | NOT ALLOW
0% | E&I | H14174239 | 6M - Maintenance and Critical Function Test Nitrogen Generator & Booster, HT-NG | ThangTD |  | PM | HT-NG | HT-62-NITROGEN |  |  |  |  | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-01 | 2025-12-31 | 2232772 | Y | NOT ALLOW
0% | E&I | H14173418 | 12 M - PM for PQP heat tracing system and Ex inspection, HT-HT-7929 | MinhNC |  | PM | HT-HT-7929 | HT-77-ELECT-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 150 | 150 | 2025-12-01 | 2025-12-31 | 2231130 | Y | NOT ALLOW
0% | E&I | H14175252 | 12M - PM for system 96XX MT1 -PCS-9601/9602 panel, MT1 | TuenNH |  | PM | MT1 | [5 empty] | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2234798 | Y | NOT ALLOW
0% | E&I | H14174134 | 12M - PM PCS devices for Open Drain HT1, HT1-HODS | NgocNH | New justify | PM | HT1-HODS | HT1-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2232562 | Y | NOT ALLOW
0% | E&I | H14175420 | 06M - PM SDS devices for chemical system on HT1, HT1-CIS | NgocNH |  | PM | HT1-CIS | HT1-49-CHEM-INJECT |  |  |  |  | SCHED | Medium (2) |  |  | 23 | 23 | 2025-12-01 | 2025-12-31 | 2235134 | Y | NOT ALLOW
0% | E&I | H14174128 | 12M - PM Heater Open Drain HT1, HT1-HODS | BanPV |  | PM | HT1-HODS | HT1-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-01 | 2025-12-31 | 2232550 | Y | NOT ALLOW
0% | E&I | H14174306 | 6M - Maintenance and CFT Fuel Gas train B PQP, HT-SK-4000B | NgocNH |  | PM | HT-SK-4000B | HT-40-FUEL-GAS |  |  |  |  | SCHED | Medium (2) |  |  | 16 | 16 | 2025-12-01 | 2025-12-31 | 2232906 | Y | NOT ALLOW
0% | E&I | H14174215 | 6M - Maintenance and Critical Function Test Fuel Gas, MT1-SK-4010 | TuenNH |  | PM | MT1-SK-4010 | MT1-40-FUEL-GAS |  |  |  |  | SCHED | Medium (2) |  |  | 7.5 | 7.5 | 2025-12-01 | 2025-12-31 | 2232724 | Y | NOT ALLOW
0% | E&I | H14175237 | 06M - Maintenance and Critical Function Test SLOT 15, HT1-WH-0115 | MinhND |  | PM | HT1-WH-0115 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2234768 | Y | NOT ALLOW
0% | E&I | H14174470 | 12M - PM PCS Instrument Devices Open Drain PQP, HT-T-5610 | HaiDQ | New justify | PM | HT-T-5610 | HT-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 18 | 10.5 | 2025-12-01 | 2025-12-31 | 2233234 | Y | NOT ALLOW
0% | E&I | H14175222 | 06M - Maintenance and Critical Function Test SLOT 14, HT1-WH-0114 | MinhND |  | PM | HT1-WH-0114 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 5.5 | 5.5 | 2025-12-01 | 2025-12-31 | 2234738 | Y | NOT ALLOW
0% | E&I | H14174464 | 12M - PM Heater Open Drain PQP, HT-T-5610 | MinhNC |  | PM | HT-T-5610 | HT-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 8 | 8 | 2025-12-01 | 2025-12-31 | 2233222 | Y | NOT ALLOW
0% | E&I | H14174546 | 6M - CFT SDS Instrument Devices Open Drain PQP, HT-T-5610 | NgocNH |  | PM | HT-T-5610 | HT-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2233386 | Y | NOT ALLOW
0% | E&I | H14174194 | 12M - PM Electrical devices for Open Drain HT1, HT1-HODS | BanPV |  | PM | HT1-HODS | HT1-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2232682 | Y | NOT ALLOW
0% | E&I | H14174363 | 6M - Maintenance and Critical Function Test Fuel gas supply, distribution and pre-heater, HT-FUELGAS | ThangTD |  | PM | HT-FUELGAS | HT-40-FUEL-GAS |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2233020 | Y | NOT ALLOW
0% | E&I | H14174699 | 12 M PM for Electrical System / lighting & small power MT1-DPA-7756, MT1-DPA-7756 | TuenNH |  | PM | MT1-DPA-7756 | MT1-77-ELECT-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 51 | 51 | 2025-12-01 | 2025-12-31 | 2233692 | Y | NOT ALLOW
0% | E&I | H14174621 | 12M - Maintenance and Functional Test Instrument devices for MT1 Diesel Storge and Distribution System, MT1-DSAD | TuenNH |  | PM | MT1-DSAD | MT1-63-DIESELSTORAGE |  |  |  |  | SCHED | Medium (2) |  |  | 13.3833 | 13.3833 | 2025-12-01 | 2025-12-31 | 2233536 | Y | NOT ALLOW
0% | E&I | H14174092 | 6M - Maintenance and Critical Function Test Closed Drain HT1, HT1-CDS | ThangTD |  | PM | HT1-CDS | HT1-55-CLOSED-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 10 | 10 | 2025-12-01 | 2025-12-31 | 2232478 | Y | NOT ALLOW
0% | E&I | H14175468 | 12M PM PCS devices for Chemical injection system, HT1-CIS | NgocNH | New justify | PM | HT1-CIS | HT1-49-CHEM-INJECT |  |  |  |  | SCHED | Medium (2) |  |  | 120 | 42 | 2025-12-01 | 2025-12-31 | 2235230 | Y | NOT ALLOW
0% | E&I | H14175292 | 12M - PM for system PQP HT-SK-4930: electrical & instrument device, HT-CI | HaiDQ |  | PM | HT-CI | HT-49-CHEM-INJECT |  |  |  |  | SCHED | Medium (2) |  |  | 32 | 32 | 2025-12-01 | 2025-12-31 | 2234878 | Y | NOT ALLOW
0% | E&I | H14175207 | 06M - Maintenance and Critical Function Test SLOT 13, HT1-WH-0113 | MinhND |  | PM | HT1-WH-0113 | HT1-01-WELLHEAD |  |  |  |  | SCHED | Medium (2) |  |  | 6 | 6 | 2025-12-01 | 2025-12-31 | 2234708 | Y | NOT ALLOW
0% | E&I | H14174525 | 12M - PM Electrical devices for Open Drain PQP, HT-T-5610 | BanPV |  | PM | HT-T-5610 | HT-56-OPEN-DRAIN |  |  |  |  | SCHED | Medium (2) |  |  | 20 | 20 | 2025-12-01 | 2025-12-31 | 2233344 | Y | NOT ALLOW
0% | E&I | H14186861 | 1M - Visual check and Function test for Hotline telephones, Inmarsat and VSAT systems, HT-90-TELECOM-SYS |  | Radio làm | CFT | HT-90-TELECOM-SYS | HT-90-TELECOM-SYS |  |  |  |  | SCHED | Medium (2) |  |  | 15 | 0 | 2025-12-08 | 2025-12-31 | 2258190 | Y | NOT ALLOW
0% | E&I | H14155148 | 8M Replace battery for HT1 corrosion probe data retrieve, | MinhNC |  | PM | [6 empty] | DFAPPR | Medium (2) |  |  | 5 | 5 | 2025-12-01 08:25 | 2025-12-30 08:26 | 2194434 | Y | NOT ALLOW
0% | E&I | P13436666 | Implement TCR HT-01-TCR-0352 To install the additional Calibration Ring for Pressure gauge MT1 system 55 | TuenNH |  | MoD | MT1-PG-5520A | MT1-55-CLOSED-DRAIN |  |  |  |  | APPR | Medium (2) |  | TAPTV | 16 | 16 | 2025-10-01 08:14 | 2025-12-31 08:14 | 288253 | Y | N
0% | E&I | P13463432 | Water proof for out door junction boxes of EGC #1 | TapTV |  | General | HT-SK-2600 | HT-26-GAS-EXP-COMPS |  |  |  |  | APPR | Medium (2) |  |  | 0 | 60 | 2025-10-01 13:53 | 2025-12-31 08:23 | 523785 | Y | N
0% | E&I | P13463156 | Replace HT1-PG-0301 due to Incorrect reading |  | Chưa có vật tư | General | HT1-PG-0301 | HT1-03-TEST-MANIFOLD |  |  |  |  | APPR | Medium (2) |  | SONNA | 5 | 0 | 2025-12-01 06:30 | 2025-12-31 18:30 | 523193 | Y | N
0% | E&I | P13465970 | Check and troubleshoot HT1 drilling deck CCTV HT1-CEA-9420 get short circuit and cause trip MCB#CAM10 |  | Done | CM | HT1-CAE-9420 | HT1-90-TELECOM-SYS | 2025-12-01 06:28 | 2025-12-15 06:28 |  |  | APPR | Medium (2) |  |  | 21 | 0 | 2025-12-01 06:28 | 2025-12-31 06:28 | 529027 | N | N
0% | E&I | P13465754 | Remove HT1-GT-0107 Well 2P replace for Well 5P |  | Done | CM | HT1-GT-0107 | HT1-01-WELLHEAD | 2025-12-01 | 2025-12-31 |  |  | APPR | Low (1) |  | VIETLV | 10 | 0 | 2025-12-01 | 2025-12-31 | 528585 | N | N
0% | E&I | P13455242 | Replace the PG of HT-HVAC-7131 compressor Train A |  | Done | CM | HT-PGH-7104A | PQP-HVAC | 2024-12-01 08:53 | 2025-12-31 08:53 |  |  | APPR | Low (1) | DUNGLV |  | 3 | 0 | 2024-12-01 08:53 | 2025-12-31 08:53 | 447889 | N | N
0% | E&I | P13461214 | Replace pressure gauge for MT1-LCV-8020 due to failure. | TuenNH |  | CM | MT1-LCV-8020 | MT1-80-FIRE-WATER | 2025-05-01 08:54 | 2025-12-31 08:54 |  |  | APPR | Low (1) |  |  | 3 | 3 | 2025-05-01 08:54 | 2025-12-31 08:54 | 511489 | N | N
0% | E&I | P13459241 | CLEAR OBS 2728 - Replace pressure gauge for walkin chiller |  | Chưa có vật tư | CM | HT-ACCU-CF-11-567 | PQP-HVAC |  |  |  |  | APPR | Low (1) | SONNM |  | 6 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 490009 | Y | N
0% | E&I | P13463792 | Bóng đèn UV đã bị hỏng cần thay thế mới |  | Chưa có vật tư | CM | MT1-UV-6010 | MT1-60-FRESH-WATER |  |  |  |  | APPR | Low (1) |  |  | 10 | 0 | 2025-12-01 14:45 | 2025-12-31 14:45 | 524523 | Y | N
0% | E&I | P13462775 | Replace MT1-PG-0914 due to broken the diaphragm surface |  | Chưa có vật tư | CM | MT1-PG-0914 | MT1-09-FLUIDLAUNCHER |  |  |  |  | APPR | Low (1) |  |  | 5.5 | 0 | 2025-12-01 06:36 | 2025-12-31 06:36 | 522407 | Y | N
0% | E&I | P13465518 | Troubleshoot HT-GDR-9715 due to failed |  | Chưa có vật tư | CM | HT-GDR-9715 | HT-97-FIRE-GAS-SYS |  |  |  |  | APPR | Low (1) | DONGPD |  | 10 | 0 | 2025-12-01 09:09 | 2025-12-31 09:09 | 528109 | Y | N
0% | E&I | P13458956 | Corrosion control panel HT1-CP-3620 RDC install for MT1-CP-0910, need to buy material to re-instate |  | Chưa có vật tư | General | HT1-CP-3620 | HT1-29-GAS-EXP-LAUNC | 2025-12-03 06:30 | 2025-12-31 18:30 |  |  | APPR | Low (1) |  |  | 10.5 | 0 | 2025-12-03 06:30 | 2025-12-31 18:30 | 486649 | N | N
0% | E&I | P13463207 | Trial test for ROC function block on PCS system |  |  | MoD | HT-PCS-9600 | HT-96-PCS-SYSTEM |  |  |  |  | APPR | Low (1) |  |  | 5 | 5 | 2025-12-01 06:30 | 2025-12-31 06:30 | 523297 | Y | N
0% | E&I | P13464149 | Return to original MOC #P13464148 (TCR #0595) - Temporary modify to control individual lighting in room 301 and 214 – PQP LQ | BanPV |  | MoD | HT-DPA-7720 | HT-77-ELECT-SYS |  |  |  |  | APPR | Low (1) |  |  | 12 | 12 | 2025-12-01 16:41 | 2025-12-08 16:45 | 525237 | Y | N
0% | E&I | P13464076 | Sent motor HT-KM-2620D EGC#1 to shore for overhaul |  | Chưa có vật tư | REC | HT-2600-M-3221 | HT-26-GAS-EXP-COMPS | 2025-09-01 17:25 | 2025-12-31 17:25 |  |  | APPR | Low (1) | CONGNP |  | 5 | 0 | 2025-09-01 17:25 | 2025-12-31 17:25 | 525091 | N | N
0% | E&I | P13462795 | Sent failure Radar component HT-ARPA-9029 to shore for repair |  | Chưa làm tháng này | REC | HT-ARPA-9029 | HT-90-TELECOM-SYS |  |  |  |  | APPR | Low (1) | DUONGVQ |  | 21 | 0 | 2025-07-01 06:30 | 2025-12-31 18:30 | 522471 | Y | N
0% | E&I | P13462925 | HT-FCV-4142 working unstable, need to check and fix. |  |  | CM | HT-FCV-4142 | PQP-REFRIGERATION | 2025-12-01 | 2025-12-31 |  |  | SCHED | Low (1) |  |  | 11 | 11 | 2025-12-01 | 2025-12-31 | 522731 | N | N
30% | E&I | P13459220 | Follow up WO:P13444754 to Troubleshoot HT-PM-6765B low insulation | BanPV |  | CM | HT-PM-6765B | HT-67-SEWAGE-SYSTEM | 2025-12-01 08:36 | 2025-12-31 08:36 |  |  | SCHED | Low (1) |  |  | 34 | 34 | 2025-12-01 08:36 | 2025-12-31 08:36 | 489649 | N | N
60% | E&I | P13460426 | Install new motor for HT-K-7161A3 TCR-PQP-71-TCR-563 |  |  | MoD | HT-K-7161A3 | PQP-HVAC |  |  |  |  | SCHED | Low (1) |  | HAIDQ | 20 | 20 | 2025-12-01 09:17 | 2025-12-31 09:17 | 503229 | Y | N
0% | E&I | P13451319 | Replace Electronic /Display module for HT1-PT-4955C |  | Chưa có vật tư | CM | HT1-PT-4955C | HT1-49-CHEM-INJECT | 2025-12-01 08:12 | 2025-12-31 08:12 |  |  | WMATL | Low (1) | DONGPD |  | 4 | 0 | 2025-12-01 08:12 | 2025-12-31 08:12 | 413609 | N | N
0% | E&I | P13463380 | MT1-PT-4955B reading incorrectly need to check and fix. | TuenNH |  | CM | MT1-PT-4955B | MT1-49-CHEM-INJECT | 2025-12-01 08:13 | 2025-12-31 08:13 |  |  | WMATL | Low (1) |  |  | 8 | 8 | 2025-12-01 08:13 | 2025-12-31 08:13 | 523681 | N | N
0% | E&I | P13442261 | Vòng nhựa cố định pin số 47 và 48 của control wiring plug X0 bị hỏng- |  | Chưa có vật tư | CM | HT-VCB-L08 | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | CONGNP |  | 5 | 0 | 2025-10-01 08:49 | 2025-12-31 07:58 | 350977 | Y | N
0% | E&I | P13448582 | Transmitter HT-PDT-4015B failure need replacement |  | Chưa có vật tư | CM | HT-PDT-4015B | HT-40-FUEL-GAS |  |  |  |  | WMATL | Low (1) | DONGPD |  | 21 | 0 | 2025-12-01 14:04 | 2025-12-31 14:04 | 394043 | Y | N
0% | E&I | P13450432 | Replace heater for panel MT1-HT-7954 |  | Chưa có vật tư | CM | MT1-79-HEAT-TRACING | MT1-79-MIS-ELECT-SYS |  |  |  |  | WMATL | Low (1) | SONNM |  | 4 | 0 | 2025-10-01 14:18 | 2025-12-31 15:35 | 408649 | Y | N
0% | E&I | P13449747 | Shutdown job -Ignitor cable for flare tip PQP failure need replacement |  | Chưa làm được | CM | HT-LHF | HT-50-HP-FLARE-SYS |  |  |  |  | WMATL | Low (1) |  |  | 30 | 0 | 2025-09-01 08:03 | 2025-12-31 08:03 | 405007 | Y | N
0% | E&I | P13451164 | Replace cooling fan for Glycol Circulation Pump Motor HT-PM-4525A |  | Chưa có vật tư | CM | HT-PM-4525A | HT-45-GLYCOL-REGEN |  |  |  |  | WMATL | Low (1) | CONGNP |  | 5.25 | 0 | 2025-10-01 06:30 | 2025-12-31 15:35 | 413049 | Y | N
0% | E&I | P13453431 | TAR Inspect and fix Flare Tip on Pilot B due to low insulation resistance |  | Chưa làm được | CM | MT1-FS | MT1-50-HP-FLARE |  |  |  |  | WMATL | Low (1) |  |  | 20 | 0 | 2025-09-01 17:03 | 2025-12-31 17:03 | 430619 | Y | N
0% | E&I | P13457701 | Oil sump heater HT-K-7191B Damaged need repalce new one |  | Chưa có vật tư | CM | HT-K-7191B | PQP-HVAC |  |  |  |  | WMATL | Low (1) | CONGNP |  | 4 | 0 | 2025-10-01 17:18 | 2025-12-31 15:35 | 472289 | Y | N
0% | E&I | P13457667 | Replace protection relay PR332 for feeder MCC-7702/OUT9B |  | Chưa có vật tư | CM | HT-MCC-7702/OUT9.BA01 | [5 empty] | WMATL | Low (1) | CONGNP |  | 10.5 | 0 | 2025-10-01 07:11 | 2025-12-31 15:35 | 471931 | Y | N
0% | E&I | P13457367 | Replace Surge Suppressor for Spare Starter of HT-MCC-7704 |  | Chưa có vật tư | CM | HT-MCC-7704 | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | CONGNP |  | 4 | 0 | 2025-10-01 14:16 | 2025-12-31 15:35 | 469049 | Y | N
0% | E&I | P13456718 | Replace fan cover of Glycol Circulation Pump Motor HT-PM-4525A/B/C |  | Chưa có vật tư | CM | HT-PM-4525A | HT-45-GLYCOL-REGEN |  |  |  |  | WMATL | Low (1) | CONGNP |  | 10.5 | 0 | 2024-10-01 06:30 | 2025-12-31 10:04 | 462583 | Y | N
0% | E&I | P13458322 | Replace Relay Module for MT1-SV-7602 EDG Fire Water Mist System due to failed |  | Chưa có vật tư | CM | MT1-EG | MT1-76-EMERG-POWER |  |  |  |  | WMATL | Low (1) | DUNGLV |  | 3 | 0 | 2025-10-01 08:52 | 2025-12-31 15:35 | 477459 | Y | N
0% | E&I | P13457556 | Replace Measuring Module for ACB Bustie of HT-MCC-7702 |  | Chưa có vật tư | CM | HT-MCC-7702-BT | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | CONGNP |  | 10.5 | 0 | 2025-12-01 14:12 | 2025-12-31 14:12 | 470929 | Y | N
0% | E&I | P13457760 | Defroster heater North crane HT-CR-7321-G4 damaged need replace | MinhNC |  | CM | HT-CR-7321-G4 | HT-73-MECHHANDLING |  |  |  |  | WMATL | Low (1) | SONNM |  | 10.5 | 10.5 | 2025-10-01 20:48 | 2025-12-31 15:35 | 472813 | Y | N
0% | E&I | P13461127 | Replace Components malfunction of CV, SDV, BDV |  | Chưa có vật tư | CM | BD1 | [5 empty] | WMATL | Low (1) |  |  | 52.5 | 0 | 2025-12-01 06:30 | 2025-12-31 18:30 | 510329 | Y | N
0% | E&I | P13460846 | Replace end lamp socket light for HT-UV-6030 |  | Chưa có vật tư | CM | HT-UV-6030 | HT-60-FRESH-WATER |  |  |  |  | WMATL | Low (1) |  |  | 5 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 507569 | Y | N
0% | E&I | P13460479 | Replace fan cooling for motor of sewage system MT1. |  | Chưa có vật tư | CM | MT1-STS | MT1-67-SEWAGE-SYSTEM |  |  |  |  | WMATL | Low (1) | CONGNP |  | 0 | 0 | 2025-12-01 14:42 | 2025-12-31 18:30 | 503787 | Y | N
0% | E&I | P13460927 | CLEAR OBS card 629 Replace pressure gauge for HVAC LV/HV & GO |  | Chưa có vật tư | CM | HT-HVAC | PQP-HVAC |  |  |  |  | WMATL | Low (1) | SONNM |  | 0 | 0 | 2025-12-01 08:14 | 2025-12-31 08:14 | 508209 | Y | N
0% | E&I | P13461061 | Replace door switch for air inlet filter enclosure EGC#1 |  | Chưa có vật tư | CM | HT-2600-ZS-6310 | HT-26-GAS-EXP-COMPS |  |  |  |  | WMATL | Low (1) |  |  | 4 | 0 | 2025-12-01 11:10 | 2025-12-31 07:40 | 509859 | Y | N
0% | E&I | P13461188 | HT-7510-PS-6685 was fail when PM F&G System for GTG#1, need to replace by new one. |  | Chưa có vật tư | CM | HT-7510-PS-6685 | HT-75-POWER-GEN |  |  |  |  | WMATL | Low (1) |  |  | 10 | 0 | 2025-12-01 07:24 | 2025-12-31 07:24 | 511089 | Y | N
0% | E&I | P13460366 | Troubleshoot lighting in HT-DPA-7713/HT-DPA-7720/HT-DPA-7730 due to failed need fixed | BanPV |  | CM | HT-DPA-7730 | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | DUNGLV |  | 17 | 17 | 2025-02-14 08:58 | 2025-12-31 08:58 | 502593 | Y | N
0% | E&I | P13462441 | Replace battery for corrosion data probe HT1-CP-2910 (ID3) and HT1-CP-0910 (ID2) |  | Chưa có vật tư | CM | HT1-CP-0910 | HT1-29-GAS-EXP-LAUNC |  |  |  |  | WMATL | Low (1) |  |  | 5 | 0 | 2025-12-01 15:16 | 2025-12-31 15:16 | 521289 | Y | N
0% | E&I | P13461836 | Replace Heater Contactor CT2 of Tumble Dryer B |  | Chưa có vật tư | CM | HT-L-7001B | HT-70-LQ-EQUIPMENT |  |  |  |  | WMATL | Low (1) | CONGNP |  | 4.5 | 0 | 2025-12-01 09:13 | 2025-12-31 09:13 | 516985 | Y | N
0% | E&I | P13461986 | Check and troubleshooted the HT-GL-7005/COOKING RANGE WITH OVEN due to trip. |  | Chưa có vật tư | CM | HT-GL-7005 | HT-70-LQ-EQUIPMENT |  |  |  |  | WMATL | Low (1) |  | MINHNC | 10.5 | 0 | 2025-12-01 08:53 | 2025-12-31 08:50 | 518049 | Y | N
0% | E&I | P13462699 | HT-7520-PS-6685 for the water mist system has a leak on its body |  | Chưa có vật tư | CM | HT-7520-PS-6685 | HT-75-POWER-GEN |  |  |  |  | WMATL | Low (1) |  |  | 10.5 | 0 | 2025-12-01 14:54 | 2025-12-31 14:54 | 522255 | Y | N
0% | E&I | P13462555 | Replace the damaged cooling fan covers of motors on PQP & HT1 |  | Chưa có vật tư | CM | HT-PM-4215A | HT-42-HEATINGMEDIUM |  |  |  |  | WMATL | Low (1) | CONGNP |  | 42 | 0 | 2025-12-01 17:13 | 2025-12-31 17:13 | 521915 | Y | N
0% | E&I | P13463748 | Wind speed of PQP North Crane damage need check and replace |  | Chưa có vật tư | CM | HT-CR-7321-B17 | HT-73-MECHHANDLING |  |  |  |  | WMATL | Low (1) | DUNGLV |  | 10.5 | 0 | 2025-12-01 06:30 | 2025-12-31 22:05 | 524417 | Y | N
0% | E&I | P13446957 | Check and troubleshoot wipe of HT-CAE-9426 |  |  | CM | HT-CAE-9426 | HT-90-TELECOM-SYS |  |  |  |  | WMATL | Low (1) | CHINHLT | HUNGPT | 10 | 10.5 | 2025-10-01 16:13 | 2025-12-31 15:35 | 384643 | Y | N
0% | E&I | P13456078 | Cover of the lattern HT-NA-9713 has many crack marks. Need to replace. |  | Chưa có vật tư | CM | HT-NA-7913 | HT-79-MIS-ELECT-SYS |  |  |  |  | WMATL | Low (1) | CHINHLT |  | 4 | 0 | 2025-09-01 13:01 | 2025-12-31 13:01 | 455009 | Y | N
0% | E&I | P13460850 | Replace Limit Switch for MT1-SSV-0105 due to valve show traveling |  | Chưa có vật tư | CM | MT1-SSV-0105 | MT1-01-WHC-SYSTEM |  |  |  |  | WMATL | Low (1) | SONNM |  | 6 | 0 | 2025-12-01 09:04 | 2025-12-31 09:04 | 507649 | Y | N
0% | E&I | P13460874 | Replace Limit Switch "FULLY OPEN" for HT1-SSV-0111 |  | Chưa có vật tư | CM | HT1-SSV-0111 | HT1-01-WELLHEAD |  |  |  |  | WMATL | Low (1) | SONNM |  | 4.5 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 507909 | Y | N
0% | E&I | P13460705 | Replace the base plates for mounting the MAC/ESD |  | Chưa có vật tư | CM | MT1-MAC-9752 | MT1-97-FIRE-GAS-SYS |  |  |  |  | WMATL | Low (1) | DUONGLD |  | 22 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 505809 | Y | N
0% | E&I | P13462007 | Flashing beacon HT-XA-9321A damaged. Need to be replaced. |  | Chưa có vật tư | CM | HT-XA-9321A | HT-90-TELECOM-SYS |  |  |  |  | WMATL | Low (1) | DUNGLV |  | 10.5 | 0 | 2025-12-01 06:30 | 2025-12-31 18:30 | 518249 | Y | N
0% | E&I | P13447001 | Replace Socket; Extension Socket 10A/250V LIOA due to bad quality | MinhNC |  | General | HT-DPA-7713 | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | CONGNP |  | 12 | 12 | 2025-12-01 15:19 | 2025-12-31 08:56 | 384731 | Y | N
0% | E&I | P13461368 | Replace pressure gauge MT1-LPG-7111A due to failure |  | Chưa có vật tư | General | MT1-LPG-7111A | MT1-HVAC |  |  |  |  | WMATL | Low (1) |  |  | 4 | 0 | 2025-10-01 18:20 | 2025-12-31 15:35 | 513041 | Y | N
0% | E&I | P13460675 | Trial replace new thermo-stat for compressor of HVAC LV/HV |  | Chưa có vật tư | General | HT-TSH-7115B | PQP-HVAC |  |  |  |  | WMATL | Low (1) |  |  | 12 | 0 | 2025-12-01 18:30 | 2025-12-31 18:30 | 505611 | Y | N
0% | E&I | P13462031 | Install weatherproof cover for instrument devices of system 21&24 upper deck QP |  | Chưa có vật tư | General | HT-FGC | HT-21-FLASHGASCOMPR |  |  |  |  | WMATL | Low (1) |  |  | 115 | 0 | 2025-10-01 11:11 | 2025-12-31 15:35 | 518489 | Y | N
0% | E&I | P13462337 | Install weatherproof cover for dampers of HVAC on PQP |  | Chưa có vật tư | General | HT-HVAC | PQP-HVAC |  |  |  |  | WMATL | Low (1) |  |  | 100 | 0 | 2025-12-01 17:43 | 2025-12-31 17:43 | 519889 | Y | N
0% | E&I | P13462212 | Install weatherproof cover for instrument devices of system 51,60,61,62,63,82 -upper deck PQP |  | Chưa có vật tư | General | PQP | [5 empty] | WMATL | Low (1) |  |  | 50 | 0 | 2025-12-01 09:55 | 2025-12-31 09:55 | 519529 | Y | N
0% | E&I | P13462229 | Install weatherproof cover for instrument devices of system 26-upper deck PQP |  | Chưa có vật tư | General | PQP | [5 empty] | WMATL | Low (1) |  |  | 200 | 0 | 2025-12-01 10:09 | 2025-12-31 10:09 | 519563 | Y | N
0% | E&I | P13462285 | Install weatherproof cover for Junction boxes on upper deck PQP-HT1 |  | Chưa có vật tư | General | PQP | [5 empty] | WMATL | Low (1) |  |  | 100 | 0 | 2025-12-01 11:14 | 2025-12-31 11:14 | 519675 | Y | N
0% | E&I | P13462076 | Install weatherproof cover for instrument devices of system 28- Mezzanine deck PQP |  | Chưa có vật tư | General | PQP | [5 empty] | WMATL | Low (1) |  |  | 20 | 0 | 2025-10-01 15:00 | 2025-12-31 15:35 | 518649 | Y | N
0% | E&I | P13462185 | Install weatherproof cover for instrument devices of system 75-upper deck PQP |  | Chưa có vật tư | General | HT-PG | HT-75-POWER-GEN |  |  |  |  | WMATL | Low (1) |  |  | 40 | 0 | 2025-12-01 18:10 | 2025-12-31 18:10 | 519329 | Y | N
0% | E&I | P13462085 | Install weatherproof cover for instrument devices of systems on HT1 |  | Chưa có vật tư | General | HT1 | [5 empty] | WMATL | Low (1) |  |  | 45 | 0 | 2025-10-01 15:35 | 2025-12-31 15:35 | 518769 | Y | N
0% | E&I | P13462112 | Install weatherproof cover for instrument devices of system 42&44 -upper deck PQP |  | Chưa có vật tư | General | HT-HM | HT-42-HEATINGMEDIUM |  |  |  |  | WMATL | Low (1) |  |  | 40 | 0 | 2025-10-01 16:24 | 2025-12-31 07:40 | 518915 | Y | N
0% | E&I | P13462125 | Install weatherproof cover for instrument devices of system 41&44 -upper deck PQP |  | Chưa có vật tư | General | HT-REFRIGERATION | PQP-REFRIGERATION |  |  |  |  | WMATL | Low (1) |  |  | 108 | 0 | 2025-12-01 16:29 | 2025-12-31 16:29 | 518969 | Y | N
0% | E&I | P13462158 | Install weatherproof cover for instrument devices of system 45 -upper deck PQP |  | Chưa có vật tư | General | HT-GR | HT-45-GLYCOL-REGEN |  |  |  |  | WMATL | Low (1) |  |  | 88 | 0 | 2025-12-01 17:47 | 2025-12-31 17:48 | 519169 | Y | N
0% | E&I | P13439902 | Implement TCR -0352 To install the additional Calibration Rings for the Pressure Transmitter system 21 |  | Done 25% | MoD | HT-SK-2180 | HT-21-FLASHGASCOMPR |  |  |  |  | WMATL | Low (1) | NAMNH | SONNA | 80 | 60 | 2025-10-01 13:47 | 2025-12-31 13:47 | 325283 | Y | N
0% | E&I | P13447750 | Implement TCR HT-01-TCR-0352 To install the additional Calibration Ring for Pressure gauge MT1 system 55 | TuenNH |  | MoD | MT1-PT-5520A | MT1-55-CLOSED-DRAIN |  |  |  |  | WMATL | Low (1) |  |  | 32 | 32 | 2025-12-01 08:58 | 2025-12-31 08:58 | 387779 | Y | N
0% | E&I | P13458705 | Install flashing light to warning people stopp smorking when extract fan stop |  | Chưa có vật tư | MoD | HT-FNM-7136A | PQP-HVAC |  |  |  |  | WMATL | Low (1) | DUNGLV |  | 20 | 0 | 2025-10-22 07:35 | 2025-12-31 13:25 | 482969 | Y | N
0% | E&I | P13461484 | Replace limit switch + indicator /solenoid for seal gas valve EGC#12 &EGC#1 |  | Chưa có vật tư | OVERHAUL | HT-2660-XV-1600B | HT-26-GAS-EXP-COMPS |  |  |  |  | WMATL | Low (1) |  |  | 10 | 0 | 2025-12-01 07:21 | 2025-12-31 06:47 | 514011 | Y | N
0% | E&I | P13460955 | Replace gasket for Junction box to prevent water and moisture ingress |  | Chưa có vật tư | OVERHAUL | PQP | [5 empty] | WMATL | Low (1) | SONNM |  | 32 | 0 | 2025-12-01 10:54 | 2025-12-31 10:54 | 508617 | Y | N
100% | E&I | P13461966 | Re-condition for yard, anti-surge valves of export gas compressor EGC1&2 | NgocNH |  | OVERHAUL | HT-SK-2660 | HT-26-GAS-EXP-COMPS |  |  |  |  | WMATL | Low (1) | CHINHLQ |  | 24 | 24 | 2025-12-01 16:12 | 2025-12-31 16:12 | 517769 | Y | N
0% | E&I | P13448778 | Reinstall switch for spare thermalstat junction box |  | Chưa có vật tư | REC | HT-HT-7929 | HT-77-ELECT-SYS |  |  |  |  | WMATL | Low (1) | NAMNH | MINHND1 | 10 | 10 | 2025-12-01 07:37 | 2025-12-31 07:37 | 395501 | Y | N
30% | E&I | P13452983 | Troubleshoot MT1 Racon due to error |  | Chưa có vật tư | REC | MT1-RAC-9000 | MT1-90-TELECOM-SYS |  |  |  |  | WMATL | Low (1) | DUNGLV | CHINHLT | 10 | 0 | 2025-10-01 13:49 | 2025-12-31 15:35 | 427773 | Y | N
0% | E&I | P13453987 | Send PQP Racon to shore for update firmware |  | Chưa có vật tư | REC | HT-RAC-9000 | HT-90-TELECOM-SYS |  |  |  |  | WMATL | Low (1) | CHINHLT |  | 20 | 0 | 2025-10-01 08:23 | 2025-12-31 15:35 | 434905 | Y | N
|  | P13466015 | General work record for E&I in Dec-2025 | [13 empty] | 170 | 170
|  | P13466026 | Fire and Gas devices loop fault, need to check at site Dec 2025 | [13 empty] | 50 | 50

## data (hidden)
WONUM | TECHPIC | ESTDUR
P13453925 |  | 40
P13456706 | HACHDD | 40
P13454944 |  | 40
P13456414 | HAITS | 241.5
P13453222 |  | 20
P13453089 |  | 30
P13453306 | DANGTH | 200
P13456437 |  | 10
P13455873 |  | 40
P13453581 | TUANNT2 | 10
H14043990 |  | 20
H14046500 |  | 20
H14046657 |  | 20
H14043982 |  | 20
H14048794 |  | 40
H14046830 |  | 20
H14045835 |  | 60
P13456392 | QUYENBN | 10
P13453902 | TUANNT2 | 32.5
P13456314 | ANHNT1 | 3470
P13453400 |  | 40
P13453451 | DANGTH | 20
P13452916 | DANGTH | 200
H14027160 | NAMVD | 120
H14043974 | TRONGHM | 10
H14043978 |  | 10
H14043966 |  | 10
H14043968 |  | 10
H14043970 |  | 10
H14043972 |  | 10
H14041291 |  | 10
H14045837 |  | 60
H14042062 |  | 10
H14043976 |  | 10
H14043952 |  | 10
H14043954 |  | 10
H14043956 |  | 10
H14043964 |  | 10
H14043958 |  | 10
H14043960 |  | 10
H14043962 |  | 10
H14045839 |  | 20
H14046628 |  | 10
H14043992 | DANGTH | 40
H14045401 |  | 80

## techname (hidden)
Tech Name
CHINHLT
BANPV
DUNGLV
TRUNGTN
LINHTT
DATPT
MINHNC
HAIDQ
LAMTH
LINHBM
NAMT
NINHNV
LENT
TAPTV
PHONGLT
TUENH
DAITH
HUNGPT
NAMBT
THANGLV
THANGTD
CUONGLV
CHANLD
NGOCNH
TRUNGNT
MINHND1
NGOCPV
VIETLV
DUNGDT
CHINHLQ
TRICDM
SONNA